## Milestones
# | Milestone | Value | Deadline | Hrs
1 | Kick off | USD 1500.00 | n/a | 0
2 | · Project Documentation | USD 1500.00 | 2017-10-23 | 75
· Database Design
· Mobile App Screen Design
3 | · Admin Backend Setup | USD 1500.00 | 2017-10-27 | 85
· iOS & Android App – Screen Integration (As much required)
4.1 | · SMS Gateway Integration | USD 750.00 | 2017-11-03 | 90
· Android App – User Registration
· Android App – Coupon Code
· Android App – Login/ Logout
· Android App – Profile Management
· Android App – Associated Users
4.2 | · iOS App – User Registration | USD 750.00 | 2017-11-03 | 90
· iOS App – Coupon Code
· iOS App – Login/ Logout
· iOS App – Profile Management
· iOS App – Associated Users
5.1 | · Android App – Drivers | USD 750.00 | 2017-11-13 | 80
· Android App – Dump Sites
· Google Map Integration
· Chat & Messaging - Setup
5.2 | · iOS App – Drivers | USD 750.00 | 2017-11-09 | 80
· iOS App – Dump Sites
6.1 | · Android App – Job Sites | USD 750.00 | 2017-11-22 | 100
· Android App – Leads
· Android App – Dashboard
· Android App – Search
6.2 | · iOS App – Job Sites | USD 750.00 | 2017-11-22 | 100
· iOS App – Leads
· iOS App – Dashboard
· iOS App – Search
7.1 | · Android App – Analytics | USD 750.00 | 2017-12-01 | 100
· Android App – Payment System
· Android App – Settings
· Chat & Messaging – Complete
7.2 | · iOS App – Analytics | USD 750.00 | 2017-12-01 | 90
· iOS App – Payment System
· iOS App – Settings
8 | · iOS & Android App - Performance Stats and History | USD 1500.00 | 2017-12-12 | 100
· Admin Backend - Complete
· User Acceptance Test
· Submit Final Apps to respective App Stores for iOS & Android
Total |  | USD 12,000.00 |  | 990
*The hours are estimates of the actual time required & includes the backend API service development as well.

## Estimates - Mobile App
Mobile App
# | Title | Services Hrs | Services Due Date | iOS Dev Hrs | iOS Dev Due Date | Android Dev Hrs | Android Dev Dur Date
0.1 | Cross Device Compatibility
1 | Splash Screen
2 | User Registration
2.1 | New Account Setup
2.2 | New account confirmation
2.3
3 | Online Payment Facility
4 | Coupon Code functional integration
4.1 | Coupon Code Apply
5 | Login/ Logout
5.1 | User Login
5.2 | Forgot Password/ Reset Password
5.3 | User Logout
6 | Profile Management
7 | Menu
8 | Job Sites
8.1 | Job Site Listing Screen
8.2 | Job site details screen
8.2 | Create Job Site Screen
New Job site creation notification.
9 | Dump Sites
9.1 | Dump Site Listing Screen |  | 7
9.2 | Dump site details screen
9.3 | Create Dump Site Screen
New Dump site creation notification.
10 | Drivers
10.1 | Drivers Listing Screen
10.2 | Drivers details screen
11 | Dashboard
11.1 | Job/ Dump Site Owner Dashboard
11.2 | Driver Dashboard
12 | Associated Users
12.1 | Associated Users
User Action Analytics
8 | Google Map Integration
12 | Chat & Messaging
13 | Financial and Performance Stats and History
Suggest Leads
Setting
Profile
Membership & Billing
Driver Settings
Master Reference Code
Help
FAQ
Contact Us
Terms & Privacy Policy
App Info
Analytical Collections

## Estimates - Backend Admin
Backend Admin
# | Title | Services Hrs | Services Due Date | Frontend Hrs | Frontend Due Date
0.1 | Cross browser Compatibility
0.2 | Responsive design & Cross device Compatibility
1 | Admin Profile and Settings Management
1.1 | Admin Login
1.2 | Forget Password & username
1.3 | Admin Profile
1.4 | Add Admin
1.5 | Admin Edit
2 | Account Management and Administration
Accounts List
Account Details
3 | Account Statistics, Performance and Metrics Data (Reports)
Payment Report
Registration Report
Expiring Accounts
Expired Accounts
Coupon Code Report
User Search Report
Associated Users Report
4 | Coupon Code Management
Add Coupon Code
Edit Coupon Code
Delete Coupon Code
5 | Review, Rating Management and Administration
Review List
6 | Settings
Review Settings
Membership Fees Management
Posting Settings
Associated Driver settings
Search Settings
7 | Leads